## MajorModule
No. | Part Number | Model | 01 FA PO |  | 02 Material Order |  | 03 Material Receiving |  | 04 CB |  | 05 BV1 |  | 06 BV2 |  | 07 Source Inspection |  | 08 FAIR Preparation |  | 09 FAIR Approval |  | 10 PRR Preparation |  | 11 PRR Approval |  | 12 Final Approval
|  |  | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual
1 | 571-267153-XXXXX | Mach I VTM |  | 완료 |  | 완료 |  | 완료 |  | 완료 |  | 완료 |  | 완료 |  | 완료 |  | 완료 |  | 2026-08-07 | 2026-08-28 |  | 2026-09-15 |  | 2026-09-30
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27

## PBX
No. | Part Number | Model | 01 FA PO |  | 02 Material Order |  | 03 Material Receiving |  | 04 CB |  | 05 BV1 |  | 06 BV2 |  | 07 LA Receiving |  | 08 LAIR Preparation |  | 09 LAIR Approval |  | 10 Source Inspection |  | 11 FAIR Preparation |  | 12 FAIR Approval |  | 13 PRR Preparation |  | 14 PRR Approval |  | 15 Final Approval
|  |  | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual
1 | 853-151282-200 | VXT-AHM |  | 완료 |  | 완료 |  | 2026-06-12 |  | 2026-08-15 | 2026-08-28 |  | 2026-09-04 | [7 empty] | 2026-09-04 |  | 2026-09-11 |  | 2026-09-16 | [5 empty] | 2026-09-30
2 | 853-154168-706 | Striker Oxide |  | 완료 |  | 완료 |  | 2026-05-23 |  | 2026-06-20 |  | 2026-07-04 | 2026-08-28 | [7 empty] | 2026-08-28 |  | 2026-09-04 |  | 2026-09-11 | [5 empty] | 2026-09-25
3 | 925-290073-614 | VXT AHM HX |  | 완료 |  | 완료 |  | 2026-04-05 |  | 2026-05-23 |  | 2026-06-08 | NA | NA | [7 empty] | 2026-06-08 |  |  |  | 완료 |  |  |  |  | 2026-09-08
4 | 853-244378-500 | STRIKER CARBIDE CK |  | 완료 |  | 완료 |  | 2026-06-13 | 2026-08-28 |  | 2026-09-04 |  | 2026-09-11 | [7 empty] | 2026-09-11 |  | 2026-09-18 |  | 2026-09-25 | [5 empty] | 2026-10-09
5 | 853-177575-015 | VCTR-XPRSMS |  | 완료 |  | 완료 | 2026-08-28 |  | 2026-08-28 |  | 2026-09-04 |  | 2026-09-11 | [7 empty] | 2026-09-11 |  | 2026-09-18 |  | 2026-09-25 | [5 empty] | 2026-10-09
6 | 575-B21019-XXXXX | RPDB |  | 완료 |  | 완료 |  | 2026-05-30 | 2026-06-12 |  |  | 2026-06-26 |  | 2026-07-04 | [7 empty] | 2026-07-04 |  |  |  | 완료 |  |  |  |  | 2026-09-08
7 | 575-B21661-XXXXX | CRPP |  | 완료 |  | 완료 |  | 2026-06-12 | 2026-07-04 |  |  | 2026-07-11 |  | 2026-07-18 | [7 empty] | 2026-07-18 |  |  |  | 완료 |  |  |  |  | 2026-09-08
8 | 925-041348-826 | ENPI |  | 완료 |  | 완료 | 2026-08-28 |  | NA | NA | 2026-08-28 |  | 2026-09-04 | [7 empty] | 2026-09-04 |  | 2026-09-11 |  | 2026-09-18 | [5 empty] | 2026-10-02
9 | 853-238341-001 | SABRE 3D |  | 완료 |  | 완료 |  | 완료 |  | 완료 |  | 완료 |  | 완료 | [7 empty] | 완료 |  | 완료 |  | 완료 |  |  |  |  | 2026-09-08
10 | 925-214137-004 | SABRE 3D |  | 완료 |  | 완료 |  | 완료 |  | 완료 |  | 완료 |  | 완료 | [7 empty] | 완료 |  | 완료 |  | 완료 |  |  |  |  | 2026-09-08
11 | 925-214137-104 | SABRE 3D |  | 완료 |  | 완료 |  | 완료 |  | 완료 |  | 완료 |  | 완료 | [7 empty] | 완료 |  | 완료 |  | 완료 |  |  |  |  | 2026-09-08
12 | 925-214138-004 | SABRE 3D |  | 완료 |  | 완료 |  | 완료 |  | 완료 |  | 완료 |  | 완료 | [7 empty] | 완료 |  | 완료 |  | 완료 |  |  |  |  | 2026-09-08
13 | 925-214138-104 | SABRE 3D |  | 완료 |  | 완료 |  | 완료 |  | 완료 |  | 완료 |  | 완료 | [7 empty] | 완료 |  | 완료 |  | 완료 |  |  |  |  | 2026-09-08
14 | 925-245250-012 | VXL-SPARC2 |  | 완료 |  | 완료 |  | 완료 | 2026-09-04 |  | 2026-09-18 |  | 2026-09-25 | [7 empty] | 2026-09-25 |  | 2026-10-02 |  | 2026-10-09 | [5 empty] | 2026-10-23
15 | XXX-290073-500 | Expedited NPI PBX Project |  | 완료 |  | 완료 |  | 완료 |  | 완료 |  | 완료 | 2026-08-29 | [7 empty] | 2026-08-29 |  | 2026-09-05 |  | 2026-09-12 | [5 empty] | 2026-09-26
16 | 857-C25324-001 | Mahabali MPD |  | 완료 |  | 완료 |  | 완료 |  | 완료 |  | 완료 |  | 완료 | [7 empty] | 완료 |  | 완료 |  | 완료 | [5 empty] | 완료
17 | 853-224690-002 | VXT-NILDS |  | 완료 |  | 완료 | 2026-08-28 |  | 2026-09-04 |  | 2026-09-18 |  | 2026-09-25 | [7 empty] | 2026-09-25 |  | 2026-10-02 |  | 2026-10-09 | [5 empty] | 2026-10-23
18 | 925-A35434-XXX | VXT-NILDS/TEOSXTI |  | 완료 |  | 완료 | 2026-08-28 |  | 2026-08-28 |  | 2026-09-11 |  | 2026-09-18 | [7 empty] | 2026-09-18 |  | 2026-09-25 |  | 2026-10-02 | [5 empty] | 2026-10-16
19 | 571-A19651-XXX | SPDB |  | 완료 |  | 완료 | 2026-09-04 |  | 2026-10-16 |  | 2026-10-30 |  | 2026-11-06 | [7 empty] | 2026-11-06 |  | 2026-11-13 |  | 2026-11-20 | [5 empty] | 2026-12-04
20 | 575-261056-001 | KIYO GX RFPP |  | 완료 |  | 완료 | 2026-09-04 |  | 2026-09-18 |  | 2026-10-02 |  | NA | [7 empty] | 2026-10-02 |  | 2026-10-09 |  | 2026-10-16 | [5 empty] | 2026-10-30
21 | 853-177575-500 | VCTR XPRS |  | 완료 |  | 완료 | 2026-09-18 |  | 2026-09-21 |  | 2026-10-16 |  | 2026-10-23 | [7 empty] | 2026-10-23 |  | 2026-10-30 |  | 2026-11-06 | [5 empty] | 2026-11-20
22 | 853-222081-005 | CVD-VXT-TEOSXT |  | 완료 |  | 완료 | 2026-09-18 |  | 2026-10-16 |  | 2026-10-30 |  | 2026-11-06 | [7 empty] | 2026-11-06 |  | 2026-11-13 |  | 2026-11-20 | [5 empty] | 2026-12-04
Formulas:
Planned = [Planned]+7
Planned = [Planned]

## EMA
No. | Part Number | 01 FA PO |  | 02 Material Order |  | 03 Material Receiving |  | 04 CB |  | 05 BV1 |  | 06 BV2 |  | 07 LA Receiving |  | 08 LAIR Preparation |  | 09 LAIR Approval |  | 10 Source Inspection |  | 11 FAIR Preparation |  | 12 FAIR Approval |  | 13 CDR |  | 14 Final Approval
|  | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual
1 | 853-043648-114
2 | 515-A46886-120
3 | 853-043648-115
4 | 853-B49960-002
5 | 853-259618-102
6 | 853-259618-202
7 | 853-181170-003
8 | 853-A57057-005
9 | 853-A57057-006
10 | 853-A57057-007
11 | 853-181170-004
12 | 853-181168-005
13 | 853-177116-006
14 | 853-181168-004
15 | 853-209194-002
16 | 853-B15113-113
17 | 853-B15113-006
18 | 853-167156-001
19 | 02-429411-00
20 | 853-160631-001
21 | 839-281618-001
22 | 853-281875-001
23 | 853-A46886-002
24 | 856-A04985-001
25 | 857-A77411-001
26 | 04-310641-00
27 | 853-240517-001
28 | 853-240517-002
29 | 02-285179-00
30 | 853-043648-211
31 | 853-043648-212
32 | 853-110997-003
33 | 853-A24821-750
34 | 853-290073-209
35 | 853-B15113-313
36 | 853-B78540-001

## 정리
Machining | Major Module |  | Power Box |  | EMA
01 FA PO | 01 FA PO |  | 01 FA PO |  | 01 FA PO
02 Material Order | 02 Material Order |  | 02 Material Order |  | 02 Material Order
03 Material Receiving | 03 Material Receiving |  | 03 Material Receiving |  | 03 Material Receiving
04 Machining (Assembly) | 04 CB | +SI | 04 CB | +SI | 04 CB | +SI
| 05 BV1 | +SI | 05 BV1 | +SI | 05 BV1 | +SI
| 06 BV2 | +SI | 06 BV2 | +SI | 06 BV2 | +SI
05 LA Receiving | LAIR 없음 |  | LAIR 주로 없음 |  | 07 LA Receiving
06 LAIR Preparation |  |  |  |  | 08 LAIR Preparation
07 LAIR Approval |  |  |  |  | 09 LAIR Approval
08 Source Inspection | 07 Source Inspection |  | 07 Source Inspection |  | 10 Source Inspection
09 FAIR Preparation | 08 FAIR Preparation | CB (포장포함) | 08 FAIR Preparation | CB (포장포함) | 11 FAIR Preparation | CB (포장포함)
10 FAIR Approval | 09 FAIR Approval |  | 09 FAIR Approval |  | 12 FAIR Approval
11 LAP Test | 10 PRR Preparation |  | PRR 거의 생략
12 CDR | 11 PRR Approval |  |  |  | 13 CDR
13 Final Approval Complete | 12 Final Approval Complete | TPM | 10 Final Approval Complete | TPM | 14 Final Approval Complete | TPM